## Tabelle1
Technology transfer project plan template
| Project name: | GeoContentAnalyser Team 2
Project leader:
| Project begin: | 2023-04-11
WP-No. | Work packages | Ressources | Month 1 | Month 2 | Month 3 | Month 4 | Remarks
Project Management
| Project planning | [5 empty] | Work packages, process, deadlines, resource allocation, (costs)
| Project controlling | [5 empty] | target-performance comparison, management activities
| Project closure | [5 empty] | Final calculation, handover/presentation, complete archiving
| Project Owner / Tutor | Prof. Dr. Ronny Weinkauf
| Kick-off workshop | [5 empty] | collaborative start
| Open science? | [5 empty] | Open source and/or open data?
| Review and feedback | [5 empty] | on-side or video call
| Handover and instruction in source code | [5 empty] | collaborative opening: source code project in IDE, build and run
| Final presentation | [5 empty] | Meeting on-side
Problem formulation
| Industrial problem/issue/needs | [5 empty] | Reports what the problem is, where it occours, and who observed it
| Context | [5 empty] | Reports environments factors such as settings and locations
| Research questions with priority | [5 empty] | Research questions or similar
| Contact persons | [5 empty] | academic and industrial
| Literature Search and Documentation | Leon Kunze |  |  |  |  | Systematic literature review OR systemic mapping study
creating p.r.d.* and Scope statement
| Planning the review | [5 empty] | SLR RQ's, Keywords, inclusion/exclusion criteria, Data extraction table
| Conducting the review | [5 empty] | search, selection, extraction, synthesis
| Reporting the review | [5 empty] | quantitative summary results in tables, discussion of principal findings
| Implications for own development | [5 empty] | Approaches available? Ideas, requirements, input …
| Software Development | Duc Hieu Le, Andrii Roshkovan, Robert Peter |  |  |  |  | Candidate Solution, developed in close collaboration (industrial partner)
| Prepare IDE and tools | [5 empty] | development environment
| Agile development | [5 empty] | Backlog, refinements, sprint (plan, do, review), version control, release
| Testing | [5 empty] | Bucktracking, Bugfixing, …
| Documentation | [5 empty] | Screenshots and screenvideos embedded in documents & presentations
| Evaluation | Astrid Rindfleisch |  |  |  |  | … not the developer, validation in academia
| Goal/Question/Metric definition | [5 empty] | Goals, objects of measurement (questions) and appropriate metrics
| Create evaluation data table | [5 empty] | set of data (appropriate metrics)
| Measurement: "new" system | [5 empty] | qualitative assurance procedures (data review/validation, consistency)
| Statistical analysis | [5 empty] | descriptive statistics (distribution etc.), data set reduction
| Statistical report | [5 empty] | explain evaluation results, limitations, inferences an lessons learnt
| Presentation | alle |  |  |  |  | present our product
| prepare presentation | [5 empty] | create the powerpoint presentation
| conduct presentation | [5 empty] | Meeting on-side
*product requirements document